## May
S.No. | DNI Package | DMA | DNI Package & sDMA | HH ( Nos) | FG Completed On | Remarks
1 | DNI Pkg 1 | 2.4 | sDMA 2.4.1 A | 507 | 17/18 Mar 2023
2 |  |  | sDMA 2.4.1 B | 475 | 14/15 Mar 2023
3 |  |  | sDMA 2.4.1 C | 711 | 17/18 Feb 2023
4 |  | 1.1 | sDMA 1.1.2 | 339 | 11/12 Apr 2023
5 |  |  | sDMA 1.1.3 | 486 | 30//1 Apr 2023
6 |  |  | sDMA 1.1.1 | 425 | 30/1 Apr 2023
7 |  | 1.4 | sDMA 1.4.1 B | 440 | 12/13 May 2023
8 |  | 6.1 | sDMA 6.1.2 | 446 | 12/13 May 2023
9 |  | 2.3 | sDMA 2.3.1 A | 483 | 3/4 May 2023
10 |  |  | sDMA 2.3.1 B | 553 | 3/4 May 2023
11 |  | 2.1 | sDMA 2.1.1 A | 418 | 17/18 May 2023
12 |  |  | sDMA 2.1.1 B | 440 | 17/18 May 2023
|  |  | S. Total | 5723
1 | DNI Pkg 2 | 3.5 | sDMA 3.5.2 | 383 | 22/23 Feb 2023
2 |  |  | sDMA 3.5.1 | 850 | 10/11 Mar 2023
3 |  | 3.4 | sDMA 3.4.1 A | 496 | 23/24 Mar 2023
4 |  |  | sDMA 3.4.1 B | 384 | 23/24 Mar 2023
5 |  | 3.3 | sDMA 3.3.1 A | 433 | 11/12 Apr 2023
6 |  |  | sDMA 3.3.1 B | 520 | 11/12 Apr 2023
7 |  |  | sDMA 3.3.1 C | 458 | 11/12 Apr 2023
8 |  |  | sDMA 3.3.1 D | 478 | 27/28 Apr 2023
9 |  |  | sDMA 3.3.1 E | 443 | 27/28 Apr 2023
10 |  | 3.2 | sDMA 3.2.1 A | 495 | 16/17 May 2023
11 |  |  | sDMA 3.2.1 B | 337 | 16/17 May 2023
12 |  |  | sDMA 3.2.1 C | 496 | 16/17 May 2023
|  |  | S. Total | 5773
1 | DNI Pkg 3 | 9.1 | sDMA 9.1.1 | 775 | 23/24 Feb 2023
2 |  |  | sDMA 9.1.2 | 1018 | 16/17 Mar 2023
3 |  |  | sDMA 9.1.3 | 544 | 8/9 Mar 2023
4 |  | 10.1 | sDMA 10.1.1 | 478 | 30/31 Mar 2023
5 |  | 9.2 | sDMA 9.2.3 | 703 | 2/3 May 2023
6 |  |  | sDMA 9.2.4 | 362 | 18/19 May 2023
7 |  |  | sDMA 9.2.5 | 427 | 18/19 May 2023
|  |  | S. Total | 4307
1 | DNI Pkg 4 | TU | TU ABC | 136 | 1/2 Sep 2022
2 |  | 1.5 | sDMA 1.5.1 | 263 | 17/18 Mar 2023
3 |  |  | sDMA 1.5.2 | 351 | 15/16 May 2023
4 |  | 7.1 | sDMA 7.1.2 | 781 | 21/22 Feb 2023
5 |  |  | sDMA 7.1.1 | 1535 | 17/18 Apr 2023
6 |  | 5.1 | sDMA 5.1.1 | 562 | 12/13 May 2023
|  |  | S. Total | 3628
|  |  | G Total | 19431
|  |  | DNI Pkg 1 | 5723
|  |  | DNI Pkg 2 | 5773
|  |  | DNI Pkg 3 | 4307
|  |  | DNI Pkg 4 | 3628
|  |  | G Total | 19431

## Jun
S.No. | DNI Package | DMA | DNI Package & sDMA | HH ( Nos) | FG Completed On | Remarks
1 | DNI Pkg 1 | 2.4 | sDMA 2.4.1 A | 507 | 17/18 Mar 2023
2 |  |  | sDMA 2.4.1 B | 475 | 14/15 Mar 2023
3 |  |  | sDMA 2.4.1 C | 711 | 17/18 Feb 2023
4 |  | 1.1 | sDMA 1.1.2 | 339 | 11/12 Apr 2023
5 |  |  | sDMA 1.1.3 | 486 | 30//1 Apr 2023
6 |  |  | sDMA 1.1.1 | 425 | 30/1 Apr 2023
7 |  | 1.4 | sDMA 1.4.1 B | 440 | 12/13 May 2023
8 |  | 6.1 | sDMA 6.1.2 | 446 | 12/13 May 2023
9 |  | 2.3 | sDMA 2.3.1 A | 483 | 3/4 May 2023
10 |  |  | sDMA 2.3.1 B | 553 | 3/4 May 2023
11 |  | 2.1 | sDMA 2.1.1 A | 418 | 17/18 May 2023
12 |  |  | sDMA 2.1.1 B | 440 | 17/18 May 2023
|  |  | S. Total | 5723
1 | DNI Pkg 2 | 3.5 | sDMA 3.5.2 | 383 | 22/23 Feb 2023
2 |  |  | sDMA 3.5.1 | 850 | 10/11 Mar 2023
3 |  | 3.4 | sDMA 3.4.1 A | 496 | 23/24 Mar 2023
4 |  |  | sDMA 3.4.1 B | 384 | 23/24 Mar 2023
5 |  | 3.3 | sDMA 3.3.1 A | 433 | 11/12 Apr 2023
6 |  |  | sDMA 3.3.1 B | 520 | 11/12 Apr 2023
7 |  |  | sDMA 3.3.1 C | 458 | 11/12 Apr 2023
8 |  |  | sDMA 3.3.1 D | 478 | 27/28 Apr 2023
9 |  |  | sDMA 3.3.1 E | 443 | 27/28 Apr 2023
10 |  | 3.2 | sDMA 3.2.1 A | 495 | 16/17 May 2023
11 |  |  | sDMA 3.2.1 B | 337 | 16/17 May 2023
12 |  |  | sDMA 3.2.1 C | 496 | 16/17 May 2023
|  |  | S. Total | 5773
1 | DNI Pkg 3 | 9.1 | sDMA 9.1.1 | 775 | 23/24 Feb 2023
2 |  |  | sDMA 9.1.2 | 1018 | 16/17 Mar 2023
3 |  |  | sDMA 9.1.3 | 544 | 8/9 Mar 2023
4 |  | 10.1 | sDMA 10.1.1 | 478 | 30/31 Mar 2023
5 |  | 9.2 | sDMA 9.2.3 | 703 | 2/3 May 2023
6 |  |  | sDMA 9.2.4 | 362 | 18/19 May 2023
7 |  |  | sDMA 9.2.5 | 427 | 18/19 May 2023
|  |  | S. Total | 4307
1 | DNI Pkg 4 | TU | TU ABC | 136 | 1/2 Sep 2022
2 |  | 1.5 | sDMA 1.5.1 | 263 | 17/18 Mar 2023
3 |  |  | sDMA 1.5.2 | 351 | 15/16 May 2023
4 |  | 7.1 | sDMA 7.1.2 | 781 | 21/22 Feb 2023
5 |  |  | sDMA 7.1.1 | 1535 | 17/18 Apr 2023
6 |  | 5.1 | sDMA 5.1.1 | 562 | 12/13 May 2023
|  |  | S. Total | 3628
|  |  | G Total | 19431
|  |  | DNI Pkg 1 | 5723
|  |  | DNI Pkg 2 | 5773
|  |  | DNI Pkg 3 | 4307
|  |  | DNI Pkg 4 | 3628
|  |  | G Total | 19431

## Aug
S.No. | DNI Package | DMA | DNI Package & sDMA | HH ( Nos) | FG Completed On | Remarks
1 | PACKAGE 1: Hangzhou-Kalika J/V | 1.1 | sDMA 1.1.1 | 425 | 30/1 Apr 2023 | 5 | 15
2 |  |  | sDMA 1.1.2 | 339 | 11/12 Apr 2023 | 4 | 14
3 |  |  | sDMA 1.1.3 | 486 | 30//1 Apr 2023 | 5 | 1
4 |  | 1.2 | sDMA 1.2.1 | 614
5 |  |  | sDMA 1.2.2 | 527
6 |  |  | sDMA 1.2.3 | 1096
7 |  | 1.3 | sDMA 1.3.1 | 1447
8 |  |  | sDMA 1.3.2 | 1835
9 |  | 1.4 | sDMA 1.4.1A | 197
10 |  |  | sDMA 1.4.1 B | 440 | 12/13 May 2023 | 7
11 |  |  | sDMA 1.4.1.C | 795
12 |  |  | sDMA 1.4.2 | 1648
13 |  | 2.1 | sDMA 2.1.1 A | 420 | 17/18 May 2023 | 8 | 4
14 |  |  | sDMA 2.1.1 B | 440 | 17/18 May 2023
15 |  |  | sDMA 2.1.2.A | 522
16 |  |  | sDMA 2.1.2 B | 132
17 |  |  | sDMA 2.1.3.A | 473
18 |  |  | sDMA 2.1.3.B | 320
19 |  |  | sDMA 2.1.4 | 288
20 |  | 2.2 | sDMA 2.2.1 | 750
21 |  |  | sDMA 2.2.2 | 933
22 |  |  | sDMA 2.2.3 | 2009
23 |  |  | sDMA 2.2.4 | 592
24 |  | 2.3 | sDMA 2.3.1 A | 513 | 3/4 May 2023 | 6 | 20
25 |  |  | sDMA 2.3.1 B | 589 | 3/4 May 2023
26 |  | 2.4 | sDMA 2.4.1 A | 507 | 17/18 Mar 2023 | 3 | 10
27 |  |  | sDMA 2.4.1 B | 475 | 14/15 Mar 2023 | 2 | 8
28 |  |  | sDMA 2.4.1 C | 711 | 17/18 Feb 2023 | 1 | 2
29 |  | 6.1 | sDMA 6.1.1 | 1859
30 |  |  | sDMA 6.1.2 | 446 | 12/13 May 2023 | 9 | 1
31 |  |  | sDMA 6.1.3 | 1320
32 |  | 6.2 | sDMA 6.2.1 | 2519
33 |  |  | sDMA 6.2.2 | 862
34 |  |  | sDMA 6.2.3 | 934
|  |  | S. Total | 27463
1 | PACKAGE 2: Hangzhou Sharma JV | 3.5 | sDMA 3.5.2 | 383 | 22/23 Feb 2023 | 1 | 4
2 |  |  | sDMA 3.5.1 | 850 | 10/11 Mar 2023 | 2 | 7
3 |  | 3.4 | sDMA 3.4.1 A | 496 | 23/24 Mar 2023 | 3 | 12
4 |  |  | sDMA 3.4.1 B | 384 | 23/24 Mar 2023
5 |  | 3.3 | sDMA 3.3.1 A | 433 | 11/12 Apr 2023 | 4 | 16
6 |  |  | sDMA 3.3.1 B | 520 | 11/12 Apr 2023
7 |  |  | sDMA 3.3.1 C | 458 | 11/12 Apr 2023
8 |  |  | sDMA 3.3.1 D | 478 | 27/28 Apr 2023 | 5 | 18
9 |  |  | sDMA 3.3.1 E | 443 | 27/28 Apr 2023
10 |  | 3.2 | sDMA 3.2.1 A | 495 | 16/17 May 2023 | 6 | 3
11 |  |  | sDMA 3.2.1 B | 337 | 16/17 May 2023
12 |  |  | sDMA 3.2.1 C | 496 | 16/17 May 2023
13 |  | 3.1 | sDMA 3.1.1 | 2750
14 |  |  | sDMA 3.1.2
15 |  | 4.1 | sDMA 4.1.2 | 527
16 |  | 4.2 | sDMA 4.2.1 | 1117
17 |  |  | sDMA 4.2.2
18 |  | 5.2 | sDMA 5.2.1 | 4337
sDMA 5.2.2
19 |  |  | sDMA 5.2.3
20 |  | 7.2 | sDMA 7.2.1 | 2533
sDMA 7.2.2
21 |  |  | sDMA 7.2.3
22 |  | 7.3 | sDMA 7.3.1 | 3014
sDMA 7.3.2
23 |  |  | sDMA 7.3.3
24 |  | 7.4 | sDMA 7.4.1 | 4651
sDMA 7.4.2
sDMA 7.4.3
25
|  |  | S. Total | 24702
| PACKAGE 3: Sumec Lama JV | 8.1 | sDMA 8.1.1 | 4410
sDMA 8.1.2
sDMA 8.1.3
1 |  | 9.1 | sDMA 9.1.1 | 775 | 23/24 Feb 2023 | 1 | 5
2 |  |  | sDMA 9.1.2 | 1018 | 16/17 Mar 2023 | 3 | 9
3 |  |  | sDMA 9.1.3 | 544 | 8/9 Mar 2023 | 2 | 6
4 |  | 9.2 | sDMA 9.2.1
5 |  |  | sDMA 9.2.2
6 |  |  | sDMA 9.2.3 | 703 | 2/3 May 2023 | 5 | 19
7 |  |  | sDMA 9.2.4 | 362 | 18/19 May 2023 | 6 | 5
8 |  |  | sDMA 9.2.5 | 427 | 18/19 May 2023
9 |  |  | sDMA 9.2.3
10 |  |  | sDMA 9.2.3
11 |  | 10.1 | sDMA 10.1.1 | 478 | 30/31 Mar 2023 | 4 | 13
12 |  | 10.2 | sDMA 10.2.1 | 2083
13 |  |  | sDMA 10.2.2
|  |  | S. Total | 10800
1 | DNI Pkg 4 | TU | TU ABC | 136 | 1/2 Sep 2022 |  | 1
2 |  | 1.5 | sDMA 1.5.1 | 263 | 17/18 Mar 2023 |  | 11
3 |  |  | sDMA 1.5.2 | 351 | 15/16 May 2023 |  | 2
|  | 5.1 | sDMA 5.1.1 | 562 | 12/13 May 2023 |  | 1
|  | 7.1 | sDMA 7.1.2 | 781 | 21/22 Feb 2023 |  | 3
|  |  | sDMA 7.1.1 | 1535 | 17/18 Apr 2023 |  | 17
|  | 11.1 | sDMA 11.1.1 | 2613
4 |  |  | sDMA 11.1.2
5 |  | 11.2 | sDMA 11.2.1 | 2339
6 |  |  | sDMA 11.2.2
|  |  | S. Total | 8580
|  |  | G Total | 71545
|  |  | DNI Pkg 1 | 27463
|  |  | DNI Pkg 2 | 24702
|  |  | DNI Pkg 3 | 10800
|  |  | DNI Pkg 4 | 8580
|  |  | G Total | 71545

## Sep
15th Sep 2023
PKG | DNI | DMA | sDMA |  | HHC Nos. |  | HHC Nos. | Metered | Name of Major Places | Status | Reservoir
PACKAGE 1: Hangzhou-Kalika J/V | 1 | 1.1 | 1.1.1 | 17.94 | 1197 | 17.94 | 425 | 315 | Narayanhiti Palace Area, Naxal,Kamaladi area | FGT Completed | Panipokhari
|  |  | 1.1.2 |  |  |  | 339 | 252 | Kantipath,Jamal, Darbarmarg,Laldurbar
|  |  | 1.1.3 |  |  |  | 486 | 369 | Naxal Bhagawati, Kamal pokhari Area
|  | 1.2 | 1.2.1 | 23.53 | 1937 |  | 614 | 426 | Trichandra college area,Kamaladi,
|  |  | 1.2.2 |  |  |  | 788 |  | Charkhal, Dilibazar, Dhobidhara
|  |  | 1.2.3 |  |  |  | 143 | 113 | Tudikhel, Bhrikuti Mandav, Bagbazaar
|  | 1.3 | 1.3.1 | 17.59 | 3252 |  | 1447 |  | Sankata, Pako, Newroad, Sundhara, Bhotebahal
|  |  | 1.3.2 |  |  |  | 1835 |  | Dharara, Basantapur, Humat, Jhonche
|  | 1.4 | 1.4.1 | 22.35 | 3080 | 4.4 | 1432 | 298 | Central jail, Sundhara,
|  |  | 1.4.2 |  |  |  | 1648 |  | Jaisidebal, Lagan, Teku
| 2 | 2.1 | 2.1.1A | 33.64 | 2596 | 33.64 | 420 | 628 | East- south of Bhatbhateni, Handigaun | FGT Completed | New Mahankal
|  |  | 2.1.1B |  |  |  | 440
|  |  | 2.1.2A |  |  |  | 522 | 406 | Tangal, Dhobikhola, Kalopul
|  |  | 2.1.2B |  |  |  | 132 | 99
|  |  | 2.1.3A |  |  |  | 473 | 391 | Bhagwatibahal, Naxal, Police HQ
|  |  | 2.1.3B |  |  |  | 320 | 217
|  |  | 2.1.4 |  |  |  | 288 | 186 | North of Jain mandir to Rato pul road
|  | 2.2 | 2.2.1 | 47.24 | 4217 |  | 750 | 54 | Charkhal, Dillibazaar
|  |  | 2.2.2 |  |  |  | 1666 |  | Gyaneshwore
|  |  | 2.2.3 |  |  |  | 1975 |  | Maitidevi
|  |  | 2.2.4 |  |  |  | 592 |  | Ratopul setopul
|  | 2.3 | 2.3.1A | 13.83 | 1071 | 13.83 | 513 | 445 | Gausala-Ratopul, Oldbaneswor -Setopul | TOC
|  |  | 2.3.1B |  |  |  | 589 | 353
|  | 2.4 | 2.4.1 | 21.01 | 1693 | 21.01 | 507 | 365 | Gausala- ringroad, Pinglasthan, Tilganga | Handover
|  |  | 2.4.2 |  |  |  | 475 | 321
|  |  | 2.4.3 |  |  |  | 711 | 524
| 6 | 6.1 | 6.1.1 | 42.39 | 3301 | 8.87 | 1535 |  | Mangalbazar, Lagankhel |  | Khumaltar
|  |  | 6.1.2 |  |  |  | 446 | 262 | Lagankhel, Army Barrak, Mahalaxmisthan | FGT Completed
|  |  | 6.1.3 |  |  |  | 1320 |  | Gwarkhu, Sundhara, Industrial Area
|  | 6.2 | 6.2.1 | 49.43 | 4315 |  | 2519 |  | Pulchwok, Natole
|  |  | 6.2.2 |  |  |  | 862 |  | katakuna, Jawakhel
|  |  | 6.2.3 |  |  |  | 934 |  | Manbhawan, Patan Hospital
[7 empty] | 27146 | 6024
PACKAGE 2: Hangzhou Sharma JV | 3 | 3.1 | 3.1.1 | 38.66 | 3536 |  |  |  | Baneshwore height, Devkota marg, Om sai marga, Prabachan Marga,Prachin Marga, | on going | New Mahankal
|  |  | 3.1.2 | [5 empty] | Thapagaun, Bijulibazaar, Bhakti Thapa Sadak, Bogati Marga, Chakhu Bakhu Marg, Devkota Sadak, Lakhechaur, New Baneswor,
|  | 3.2 | 3.2.1A | 31.82 | 2826 | 31.82 | 1328 | 2421 | Old Baneswor, Bhimsen Thapa, Devkota Sadak, Dharanidhar, Jankuti Marga, Kasturi Marga | FGT Completed
3.2.1B
3.2.1C
|  |  | 3.2.2 |  |  |  | 1481 |  | Mid Baneswor, Bhimsengola Marg, North of Parliament house baneswor
|  | 3.3 | 3.3.1 A,B.C | 28.09 | 2284 | 28.09 | 1411 | 1882 | Baburam Acharya sadak, Bagmati Corridor, Bhimsengola, Katyani marg, Kumud Devkota Marga, Prakriti Marga, Prayag Marg, Santinagar | FGT Completed
|  |  | 3.3.1 D,E |  |  |  | 921
|  | 3.4 | 3.4.1 | 17.43 | 890 | 17.43 | 890 | 772 | Bagmati Corridor, Gairigau, Dhaulagiri Marg, Mayur Galli, Pranami Galli, Raja Janak Marg, Shakti Binayak Marga, Sinamangal, Tara Marga, Tinkune | FGT Completed
|  | 3.5 | 3.5.1 | 16.18 | 1233 | 16.18 | 850 | 932 | Airport,Baburam Acharya sadak. , Kalimati dol, Khahare Marg, Pashupati Marg, Shambhu Marga, Sinamangal , Tilganga | TOC
|  |  | 3.5.2 |  |  |  | 383 |  | Airport Way, Bagmati Corridor, Sinamangal, Tilganga,
| 4 | 4.1 | 4.1.1 | 7.9 | 517 |  | 555 | 518 | Singhdarbar |  | Anamnagar
|  |  | 4.1.2 | [5 empty] | Ghattekulo, Anamnagar
|  | 4.2 | 4.2.1 | 21.95 | 1117 |  | 1082 | 1027 | CDO Office, Babarmahal
|  |  | 4.2.2 | [5 empty] | Thapathali, Kuriyagaun
|  |  | 4.2.3 | [5 empty] | Bagmati corridor, Prasuti Griha
| 5 | 5.2 | 5.2.1 | 49.68 | 1593 |  | 1593 | 935 | Pembahal,Mikha bahal,Pulchowk,Krishna Galli,Patan Dhokha |  | Khumaltar
|  |  | 5.2.2 |  | 1798 |  | 1798 | 1426 | Alko Nagar,Sankhamul Plotting, Chkupat, Kumbeswor,Ikhachhen Galli, Sankhamul,Money Marg, Aaluko hiti,Manidole,Ekhachhen Galli,Chakupat
|  |  | 5.2.3 |  | 724 |  | 724 | 545 | Jwagal, Kupandol, Pulchowk, UN Park, Chakupat, Pulchowk, Jwagal, Patan dhokha
| 7 | 7.2 | 7.2.1 | 27.95 | 2895 |  |  |  | Kuslechaur, Manang Galli, Bhudeganesh Galli, Indrayani Marg |  | Balaju
|  |  | 7.2.2 | [5 empty] | Kaldhara, Ganesh Raj Marg, Paknajol, Shorakhutte, Link Road
|  |  | 7.2.3 | [5 empty] | Keshar Mahal, Bhagawan Bahal, Amrit Marg, Thamel
|  | 7.3 | 7.3.1 | 24.34 | 2002 |  |  |  | Ganesh Galli, Gangalal marg, Dukucha Galli, Burankhya, Ekhapokhari, Kumari & Ghat Galli
|  |  | 7.3.2 | [5 empty] | Gangalal Marg, Na gal , Chittadhar Marg, Bangemudha, Dhkha Baha, Tyouda, Talachi, Kwabahal, Jyatha,Jawabahal, Thamel, J.P. Marg
|  |  | 7.3.3 | [5 empty] | Jyatha, Thamel, Kantipatha, Thamel marga, Keshar mahal, Inbahal, Kunayatwa, Jamal, Ashan, Siddhidas marg
|  | 7.4 | 7.4.1 | 34.28 | 3999 |  |  |  | Ramghat, Paropakar, Kankeshwori, Damai tole, Yogbirsing marg
|  |  | 7.4.2 | [5 empty] | Ashok Binayak, Ramghat, Indrashabha marg, Layaku Chuka
|  |  | 7.4.3 | [5 empty] | Gangalal Marg, Itumbahal, Taha Nani, Yogbir Singh Marg, Bhedasing
|  |  | 7.4.4 | [5 empty] | Ashan, Jamal, Bhotaihiti, Chittadhar Marg, Bir Hospital
[5 empty] | 25507.52 |  | 13016 | 10458
PACKAGE 3: Sumec Lama JV | 8 | 8.1 | 8.1.1A | 55.14 | 3680 |  | 448 | 256 | Bhanimandal, Jawalakhel, zoo |  | Khumaltar
|  |  | 8.1.1B |  |  |  | 244 | 162
|  |  | 8.1.2A |  |  |  | 766 | 366 | Hariharbhawan, Sanepa, Kupandol
8.1.2B
8.1.2C
|  |  | 8.1.3A | [5 empty] | Kupandol, Bagmati corrodor
8.1.3B
| 9 | 9.1 | 9.1.1 | 21.74 | 2337 | 21.74 | 805 | 577 | Narephat | TOC
|  |  | 9.1.2 |  |  |  | 1025 | 864
|  |  | 9.1.3 |  |  |  | 546 | 405
|  | 9.2 | 9.2.1 | 48.14 | 3778 | 48.14 | 718 | 692 | Dovan area Koteswor | on going
|  |  | 9.2.2 |  |  |  | 606 | 645 | Koteswor Mahadevsthan Area
|  |  | 9.2.3 |  |  |  | 646 | 511 | Phulbari Area | FGT Completed
|  |  | 9.2.4 |  |  |  | 367 | 320 | SOS, Chautarphi Marg area
|  |  | 9.2.5 |  |  |  | 432 | 337 | Police station Koteswor (North) area
|  |  | 9.2.6 |  |  |  | 616 | 520 | Tinkune area (South of highway) | FGT Completed
|  |  | 9.2.7 |  |  |  | 475 | 376 | Munibhairab, Peris danda area Koteswor
| 10 | 10.1 | 10.1.1 | 11.93 | 478 | 11.93 | 478 | 408 | Dallu | FGT Completed | Balaju
|  | 10.2 | 10.2.1A | 31.82 | 2908 |  | 487 | 381 | Kumdole
|  |  | 10.2.1B |  |  |  | 296 | 250
|  |  | 10.2.1C |  |  |  | 319 | 281
|  |  | 10.2.2A |  |  |  | 361 | 253 | Shobabhagawati
|  |  | 10.2.2B |  |  |  | 315 | 231
|  |  | 10.2.2C |  |  |  | 491 | 259
[5 empty] | 13181 |  | 10441 | 8094
PACKAGE 4: GIETC- Sharma- Raman JV | 1 | 1.5 | 1.5.1 | 21.93 | 1024 | 21.93 | 262 | 237 | Maitighar, Ramshahpath, Sahidgate, Tripureswor | FGT Completed | Panipokhari
|  |  | 1.5.2 |  |  |  | 351 | 285 | South of Tripureswor-Teku road
|  |  | 1.5.3 |  |  |  | 411 | 299 | Teku, Bagmati corridor
| 5 | 5.1 | 5.1.1 | 51.88 | 565 | 18.5 | 565 | 283 | Gwarkhu, Chyasal | FGT Completed | Khumaltar
|  |  | 5.1.2 | [5 empty] | Sundhara, Shankhamul
|  |  | 5.1.3 | [5 empty] | Patan Darbar squate
| 8 | 8.2 | 8.2.1 | 39.8 | 3335 | 15.22 | 1185 | 59 | Bhanimandal | On going
|  |  | 8.2.2 | [5 empty] | Jhamsikhel/inside ringroad
| 7 | 7.1 | 7.1.1 | 29.2 | 2343 | 29.2 | 1556 | 1267 | Khusibu town planning | FGT Completed | Balaju
|  |  | 7.1.2 |  |  |  | 787 | 594 | Khusibu town planning
| 11 | 11.1 | 11.1.1 | 33 | 3907 |  |  | 0 | Kalimati/Bishnumati River side |  | Kirtipur
|  |  | 11.1.2 | [5 empty] | Ravi Bhavan
|  |  | 11.1.3 | [5 empty] | Between Kalimati And Kalanki
|  | 11.2 | 11.2.1 | 38 | 3350 |  |  | 0 | Kalanki
|  |  | 11.2.2 | [5 empty] | Link Marg
|  |  | 11.2.3 | [5 empty] | Kuleshwor
| TU | TU | TU | 10.45 | 136 | 10.45 | 136 | 0 | TU area A | TOC
|  |  | TU - B | [5 empty] | TU area B
|  |  | TU - C | [5 empty] | TU area C
|  |  |  | 980.26 | 14660 | 370.32 | 5253 | 3024
37.78%
[7 empty] | 55856 | 27600

## Oct
2023-10-09
PKG | DNI | DMA | sDMA |  | DMA wise HHC Nos. |  | sDMA wise HHC Nos. | Metered | Name of Major Places | Status | Reservoir
PACKAGE 1: Hangzhou-Kalika J/V | 1 | 1.1 | 1.1.1 | 17.94 | 1197 | 17.94 | 425 | 315 | Narayanhiti Palace Area, Naxal,Kamaladi area | FGT Completed | Panipokhari
|  |  | 1.1.2 |  |  |  | 339 | 252 | Kantipath,Jamal, Darbarmarg,Laldurbar
|  |  | 1.1.3 |  |  |  | 486 | 369 | Naxal Bhagawati, Kamal pokhari Area
|  | 1.2 | 1.2.1 | 23.53 | 1937 |  | 614 | 426 | Trichandra college area,Kamaladi,
|  |  | 1.2.2 |  |  |  | 788 |  | Charkhal, Dilibazar, Dhobidhara
|  |  | 1.2.3 |  |  |  | 143 | 113 | Tudikhel, Bhrikuti Mandav, Bagbazaar
|  | 1.3 | 1.3.1 | 17.59 | 3252 |  | 1447 |  | Sankata, Pako, Newroad, Sundhara, Bhotebahal
|  |  | 1.3.2 |  |  |  | 1835 |  | Dharara, Basantapur, Humat, Jhonche
|  | 1.4 | 1.4.1 | 22.35 | 3080 | 4.4 | 1432 | 298 | Central jail, Sundhara,
|  |  | 1.4.2 |  |  |  | 1648 |  | Jaisidebal, Lagan, Teku
| 2 | 2.1 | 2.1.1A | 33.64 | 2596 | 33.64 | 420 | 628 | East- south of Bhatbhateni, Handigaun | FGT Completed | New Mahankal
|  |  | 2.1.1B |  |  |  | 440
|  |  | 2.1.2A |  |  |  | 522 | 406 | Tangal, Dhobikhola, Kalopul
|  |  | 2.1.2B |  |  |  | 132 | 99
|  |  | 2.1.3A |  |  |  | 473 | 391 | Bhagwatibahal, Naxal, Police HQ
|  |  | 2.1.3B |  |  |  | 320 | 217
|  |  | 2.1.4 |  |  |  | 288 | 186 | North of Jain mandir to Rato pul road
|  | 2.2 | 2.2.1 | 47.24 | 4217 |  | 750 | 54 | Charkhal, Dillibazaar
|  |  | 2.2.2 |  |  |  | 1666 |  | Gyaneshwore
|  |  | 2.2.3 |  |  |  | 1975 |  | Maitidevi
|  |  | 2.2.4 |  |  |  | 592 |  | Ratopul setopul
|  | 2.3 | 2.3.1A | 13.83 | 1071 | 13.83 | 513 | 445 | Gausala-Ratopul, Oldbaneswor -Setopul | TOC
|  |  | 2.3.1B |  |  |  | 589 | 353
|  | 2.4 | 2.4.1 | 21.01 | 1693 | 21.01 | 507 | 365 | Gausala- ringroad, Pinglasthan, Tilganga | Handover
|  |  | 2.4.2 |  |  |  | 475 | 321
|  |  | 2.4.3 |  |  |  | 711 | 524
| 6 | 6.1 | 6.1.1 | 42.39 | 3301 | 8.87 | 1535 |  | Mangalbazar, Lagankhel |  | Khumaltar
|  |  | 6.1.2 |  |  |  | 446 | 262 | Lagankhel, Army Barrak, Mahalaxmisthan | FGT Completed
|  |  | 6.1.3 |  |  |  | 1320 |  | Gwarkhu, Sundhara, Industrial Area
|  | 6.2 | 6.2.1 | 49.43 | 4315 |  | 2519 |  | Pulchwok, Natole
|  |  | 6.2.2 |  |  |  | 862 |  | katakuna, Jawakhel
|  |  | 6.2.3 |  |  |  | 934 |  | Manbhawan, Patan Hospital
[5 empty] | 26758.69 |  | 27146 | 6024
PACKAGE 2: Hangzhou Sharma JV | 3 | 3.1 | 3.1.1 | 38.66 | 3536 |  | 1694 |  | Baneshwore height, Devkota marg, Om sai marga, Prabachan Marga,Prachin Marga, | on going | New Mahankal
|  |  | 3.1.2 |  |  |  | 1842 |  | Thapagaun, Bijulibazaar, Bhakti Thapa Sadak, Bogati Marga, Chakhu Bakhu Marg, Devkota Sadak, Lakhechaur, New Baneswor,
|  | 3.2 | 3.2.1A | 31.82 | 2826 | 31.82 | 1328 | 2421 | Old Baneswor, Bhimsen Thapa, Devkota Sadak, Dharanidhar, Jankuti Marga, Kasturi Marga | FGT Completed
3.2.1B
3.2.1C
|  |  | 3.2.2 |  |  |  | 1481 |  | Mid Baneswor, Bhimsengola Marg, North of Parliament house baneswor
|  | 3.3 | 3.3.1 A,B.C | 28.09 | 2284 | 28.09 | 1411 | 1882 | Baburam Acharya sadak, Bagmati Corridor, Bhimsengola, Katyani marg, Kumud Devkota Marga, Prakriti Marga, Prayag Marg, Santinagar | FGT Completed
|  |  | 3.3.1 D,E |  |  |  | 921
|  | 3.4 | 3.4.1 | 17.43 | 890 | 17.43 | 890 | 772 | Bagmati Corridor, Gairigau, Dhaulagiri Marg, Mayur Galli, Pranami Galli, Raja Janak Marg, Shakti Binayak Marga, Sinamangal, Tara Marga, Tinkune | FGT Completed
|  | 3.5 | 3.5.1 | 16.18 | 1233 | 16.18 | 850 | 932 | Airport,Baburam Acharya sadak. , Kalimati dol, Khahare Marg, Pashupati Marg, Shambhu Marga, Sinamangal , Tilganga | TOC
|  |  | 3.5.2 |  |  |  | 383 |  | Airport Way, Bagmati Corridor, Sinamangal, Tilganga,
| 4 | 4.1 | 4.1.1 | 7.9 | 517 |  | 555 | 518 | Singhdarbar |  | Anamnagar
|  |  | 4.1.2 | [5 empty] | Ghattekulo, Anamnagar
|  | 4.2 | 4.2.1 | 21.95 | 1117 |  | 1082 | 1027 | CDO Office, Babarmahal
|  |  | 4.2.2 | [5 empty] | Thapathali, Kuriyagaun
|  |  | 4.2.3 | [5 empty] | Bagmati corridor, Prasuti Griha
| 5 | 5.2 | 5.2.1 | 49.68 | 1593 |  | 1593 | 935 | Pembahal,Mikha bahal,Pulchowk,Krishna Galli,Patan Dhokha |  | Khumaltar
|  |  | 5.2.2 |  | 1798 |  | 1798 | 1426 | Alko Nagar,Sankhamul Plotting, Chkupat, Kumbeswor,Ikhachhen Galli, Sankhamul,Money Marg, Aaluko hiti,Manidole,Ekhachhen Galli,Chakupat
|  |  | 5.2.3 |  | 724 |  | 724 | 545 | Jwagal, Kupandol, Pulchowk, UN Park, Chakupat, Pulchowk, Jwagal, Patan dhokha
| 7 | 7.2 | 7.2.1 | 27.95 | 2895 |  | 1259 |  | Kuslechaur, Manang Galli, Bhudeganesh Galli, Indrayani Marg |  | Balaju
|  |  | 7.2.2 |  |  |  | 1124 |  | Kaldhara, Ganesh Raj Marg, Paknajol, Shorakhutte, Link Road
|  |  | 7.2.3 |  |  |  | 528 |  | Keshar Mahal, Bhagawan Bahal, Amrit Marg, Thamel
|  | 7.3 | 7.3.1 | 24.34 | 2002 |  | 913 |  | Ganesh Galli, Gangalal marg, Dukucha Galli, Burankhya, Ekhapokhari, Kumari & Ghat Galli
|  |  | 7.3.2 |  |  |  | 1226 |  | Gangalal Marg, Na gal , Chittadhar Marg, Bangemudha, Dhkha Baha, Tyouda, Talachi, Kwabahal, Jyatha,Jawabahal, Thamel, J.P. Marg
|  |  | 7.3.3 |  |  |  | 1356 |  | Jyatha, Thamel, Kantipatha, Thamel marga, Keshar mahal, Inbahal, Kunayatwa, Jamal, Ashan, Siddhidas marg
|  | 7.4 | 7.4.1 | 34.28 | 3999 |  | 1788 |  | Ramghat, Paropakar, Kankeshwori, Damai tole, Yogbirsing marg
|  |  | 7.4.2 |  |  |  | 821 |  | Ashok Binayak, Ramghat, Indrashabha marg, Layaku Chuka
|  |  | 7.4.3 |  |  |  | 3334 |  | Gangalal Marg, Itumbahal, Taha Nani, Yogbir Singh Marg, Bhedasing
|  |  | 7.4.4 |  |  |  | 521 |  | Ashan, Jamal, Bhotaihiti, Chittadhar Marg, Bir Hospital
[5 empty] | 25507.52 |  | 29422 | 10458
PACKAGE 3: Sumec Lama JV | 8 | 8.1 | 8.1.1A | 55.14 | 3680 |  | 448 | 256 | Bhanimandal, Jawalakhel, zoo |  | Khumaltar
|  |  | 8.1.1B |  |  |  | 244 | 162
|  |  | 8.1.2A |  |  |  | 766 | 366 | Hariharbhawan, Sanepa, Kupandol
8.1.2B
8.1.2C
|  |  | 8.1.3A | [5 empty] | Kupandol, Bagmati corrodor
8.1.3B
| 9 | 9.1 | 9.1.1 | 21.74 | 2337 | 21.74 | 805 | 577 | Narephat | TOC
|  |  | 9.1.2 |  |  |  | 1025 | 864
|  |  | 9.1.3 |  |  |  | 546 | 405
|  | 9.2 | 9.2.1 | 48.14 | 3778 | 48.14 | 718 | 692 | Dovan area Koteswor | on going
|  |  | 9.2.2 |  |  |  | 606 | 645 | Koteswor Mahadevsthan Area
|  |  | 9.2.3 |  |  |  | 646 | 511 | Phulbari Area | FGT Completed
|  |  | 9.2.4 |  |  |  | 367 | 320 | SOS, Chautarphi Marg area
|  |  | 9.2.5 |  |  |  | 432 | 337 | Police station Koteswor (North) area
|  |  | 9.2.6 |  |  |  | 616 | 520 | Tinkune area (South of highway) | FGT Completed
|  |  | 9.2.7 |  |  |  | 475 | 376 | Munibhairab, Peris danda area Koteswor
| 10 | 10.1 | 10.1.1 | 11.93 | 478 | 11.93 | 478 | 408 | Dallu | FGT Completed | Balaju
|  | 10.2 | 10.2.1A | 31.82 | 2908 |  | 487 | 381 | Kumdole
|  |  | 10.2.1B |  |  |  | 296 | 250
|  |  | 10.2.1C |  |  |  | 319 | 281
|  |  | 10.2.2A |  |  |  | 361 | 253 | Shobabhagawati
|  |  | 10.2.2B |  |  |  | 315 | 231
|  |  | 10.2.2C |  |  |  | 491 | 259
[5 empty] | 13181 |  | 10441 | 8094
PACKAGE 4: GIETC- Sharma- Raman JV | 1 | 1.5 | 1.5.1 | 21.93 | 1024 | 21.93 | 262 | 237 | Maitighar, Ramshahpath, Sahidgate, Tripureswor | FGT Completed | Panipokhari
|  |  | 1.5.2 |  |  |  | 357 | 285 | South of Tripureswor-Teku road
|  |  | 1.5.3 |  |  |  | 386 | 299 | Teku, Bagmati corridor
| 5 | 5.1 | 5.1.1 | 51.88 | 5265 | 18.5 | 565 | 283 | Gwarkhu, Chyasal | FGT Completed | Khumaltar
|  |  | 5.1.2 |  |  |  | 2600 |  | Sundhara, Shankhamul
|  |  | 5.1.3 |  |  |  | 2100 |  | Patan Darbar squate
| 8 | 8.2 | 8.2.1 | 39.8 | 3335 | 15.22 | 1185 | 59 | Bhanimandal | On going
|  |  | 8.2.2 |  |  |  | 2150 |  | Jhamsikhel/inside ringroad
| 7 | 7.1 | 7.1.1 | 29.2 | 2343 | 29.2 | 1556 | 1267 | Khusibu town planning | FGT Completed | Balaju
|  |  | 7.1.2 |  |  |  | 787 | 594 | Khusibu town planning
| 11 | 11.1 | 11.1.1 | 33 | 3907 |  | 1800 | 0 | Kalimati/Bishnumati River side |  | Kirtipur
|  |  | 11.1.2 |  |  |  | 2107 |  | Ravi Bhavan/Between Kalimati And Kalanki
|  | 11.2 | 11.2.1 | 38 | 3350 |  | 1550 | 0 | Kalanki
|  |  | 11.2.2 |  |  |  | 1800 |  | Link Marg/Kuleshwor
| TU | TU | TU | 10.45 | 136 | 10.45 | 136 | 0 | TU area A | TOC
|  |  | TU - B | [5 empty] | TU area B
|  |  | TU - C | [5 empty] | TU area C
|  |  |  | 980.26 | 19360 | 370.32 | 19341 | 3024

## Sheet1
sDMA | SDMA wise HHC | Areas | Packages
1.1.1 | 425 | Narayanhiti Palace Area, Naxal,Kamaladi area | 1
1.1.2 | 339 | Kantipath,Jamal, Darbarmarg,Laldurbar | 1
1.1.3 | 486 | Naxal Bhagawati, Kamal pokhari Area | 1
1.2.1 | 614 | Trichandra college area,Kamaladi, | 1
1.2.2 | 788 | Charkhal, Dilibazar, Dhobidhara | 1
1.2.3 | 143 | Tudikhel, Bhrikuti Mandav, Bagbazaar | 1
1.3.1 | 1447 | Sankata, Pako, Newroad, Sundhara, Bhotebahal | 1
1.3.2 | 1835 | Dharara, Basantapur, Humat, Jhonche | 1
1.4.1 | 1432 | Central jail, Sundhara, | 1
1.4.2 | 1648 | Jaisidebal, Lagan, Teku | 1
2.1.1A | 420 | East- south of Bhatbhateni, Handigaun | 1
2.1.1B | 440 |  | 1
2.1.2A | 522 | Tangal, Dhobikhola, Kalopul | 1
2.1.2B | 132 |  | 1
2.1.3A | 473 | Bhagwatibahal, Naxal, Police HQ | 1
2.1.3B | 320 |  | 1
2.1.4 | 288 | North of Jain mandir to Rato pul road | 1
2.2.1 | 750 | Charkhal, Dillibazaar | 1
2.2.2 | 1666 | Gyaneshwore | 1
2.2.3 | 1975 | Maitidevi | 1
2.2.4 | 592 | Ratopul setopul | 1
2.3.1A | 513 | Gausala-Ratopul, Oldbaneswor -Setopul | 1
2.3.1B | 589 |  | 1
2.4.1 | 507 | Gausala- ringroad, Pinglasthan, Tilganga | 1
2.4.2 | 475 |  | 1
2.4.3 | 711 |  | 1
6.1.1 | 1535 | Mangalbazar, Lagankhel | 1
6.1.2 | 446 | Lagankhel, Army Barrak, Mahalaxmisthan | 1
6.1.3 | 1320 | Gwarkhu, Sundhara, Industrial Area | 1
6.2.1 | 2519 | Pulchwok, Natole | 1
6.2.2 | 862 | katakuna, Jawakhel | 1
6.2.3 | 934 | Manbhawan, Patan Hospital | 1
3.1.1 | 1694 | Baneshwore height, Devkota marg, Om sai marga, Prabachan Marga,Prachin Marga, | 2
3.1.2 | 1842 | Thapagaun, Bijulibazaar, Bhakti Thapa Sadak, Bogati Marga, Chakhu Bakhu Marg, Devkota Sadak, Lakhechaur, New Baneswor, | 2
3.2.1A | 1328 | Old Baneswor, Bhimsen Thapa, Devkota Sadak, Dharanidhar, Jankuti Marga, Kasturi Marga | 2
3.2.1B |  |  | 2
3.2.1C |  |  | 2
3.2.2 | 1481 | Mid Baneswor, Bhimsengola Marg, North of Parliament house baneswor | 2
3.3.1 A,B.C | 1411 | Baburam Acharya sadak, Bagmati Corridor, Bhimsengola, Katyani marg, Kumud Devkota Marga, Prakriti Marga, Prayag Marg, Santinagar | 2
3.3.1 D,E | 921 |  | 2
3.4.1 | 890 | Bagmati Corridor, Gairigau, Dhaulagiri Marg, Mayur Galli, Pranami Galli, Raja Janak Marg, Shakti Binayak Marga, Sinamangal, Tara Marga, Tinkune | 2
3.5.1 | 850 | Airport,Baburam Acharya sadak. , Kalimati dol, Khahare Marg, Pashupati Marg, Shambhu Marga, Sinamangal , Tilganga | 2
3.5.2 | 383 | Airport Way, Bagmati Corridor, Sinamangal, Tilganga, | 2
4.1.1 | 555 | Singhdarbar | 2
4.1.2 |  | Ghattekulo, Anamnagar | 2
4.2.1 | 1082 | CDO Office, Babarmahal | 2
4.2.2 |  | Thapathali, Kuriyagaun | 2
4.2.3 |  | Bagmati corridor, Prasuti Griha | 2
5.2.1 | 1593 | Pembahal,Mikha bahal,Pulchowk,Krishna Galli,Patan Dhokha | 2
5.2.2 | 1798 | Alko Nagar,Sankhamul Plotting, Chkupat, Kumbeswor,Ikhachhen Galli, Sankhamul,Money Marg, Aaluko hiti,Manidole,Ekhachhen Galli,Chakupat | 2
5.2.3 | 724 | Jwagal, Kupandol, Pulchowk, UN Park, Chakupat, Pulchowk, Jwagal, Patan dhokha | 2
7.2.1 | 1259 | Kuslechaur, Manang Galli, Bhudeganesh Galli, Indrayani Marg | 2
7.2.2 | 1124 | Kaldhara, Ganesh Raj Marg, Paknajol, Shorakhutte, Link Road | 2
7.2.3 | 528 | Keshar Mahal, Bhagawan Bahal, Amrit Marg, Thamel | 2
7.3.1 | 913 | Ganesh Galli, Gangalal marg, Dukucha Galli, Burankhya, Ekhapokhari, Kumari & Ghat Galli | 2
7.3.2 | 1226 | Gangalal Marg, Na gal , Chittadhar Marg, Bangemudha, Dhkha Baha, Tyouda, Talachi, Kwabahal, Jyatha,Jawabahal, Thamel, J.P. Marg | 2
7.3.3 | 1356 | Jyatha, Thamel, Kantipatha, Thamel marga, Keshar mahal, Inbahal, Kunayatwa, Jamal, Ashan, Siddhidas marg | 2
7.4.1 | 1788 | Ramghat, Paropakar, Kankeshwori, Damai tole, Yogbirsing marg | 2
7.4.2 | 821 | Ashok Binayak, Ramghat, Indrashabha marg, Layaku Chuka | 2
7.4.3 | 3334 | Gangalal Marg, Itumbahal, Taha Nani, Yogbir Singh Marg, Bhedasing | 2
7.4.4 | 521 | Ashan, Jamal, Bhotaihiti, Chittadhar Marg, Bir Hospital | 2
8.1.1A | 448 | Bhanimandal, Jawalakhel, zoo | 3
8.1.1B | 244 |  | 3
8.1.2A | 766 | Hariharbhawan, Sanepa, Kupandol | 3
8.1.2B |  |  | 3
8.1.2C |  |  | 3
8.1.3A |  | Kupandol, Bagmati corrodor | 3
8.1.3B |  |  | 3
9.1.1 | 805 | Narephat | 3
9.1.2 | 1025 |  | 3
9.1.3 | 546 |  | 3
9.2.1 | 718 | Dovan area Koteswor | 3
9.2.2 | 606 | Koteswor Mahadevsthan Area | 3
9.2.3 | 646 | Phulbari Area | 3
9.2.4 | 367 | SOS, Chautarphi Marg area | 3
9.2.5 | 432 | Police station Koteswor (North) area | 3
9.2.6 | 616 | Tinkune area (South of highway) | 3
9.2.7 | 475 | Munibhairab, Peris danda area Koteswor | 3
10.1.1 | 478 | Dallu | 3
10.2.1A | 487 | Kumdole | 3
10.2.1B | 296 |  | 3
10.2.1C | 319 |  | 3
10.2.2A | 361 | Shobabhagawati | 3
10.2.2B | 315 |  | 3
10.2.2C | 491 |  | 3
1.5.1 | 262 | Maitighar, Ramshahpath, Sahidgate, Tripureswor | 4
1.5.2 | 357 | South of Tripureswor-Teku road | 4
1.5.3 | 386 | Teku, Bagmati corridor | 4
5.1.1 | 565 | Gwarkhu, Chyasal | 4
5.1.2 | 2600 | Sundhara, Shankhamul | 4
5.1.3 | 2100 | Patan Darbar squate | 4
8.2.1 | 1185 | Bhanimandal | 4
8.2.2 | 2150 | Jhamsikhel/inside ringroad | 4
7.1.1 | 1556 | Khusibu town planning | 4
7.1.2 | 787 | Khusibu town planning | 4
11.1.1 | 1800 | Kalimati/Bishnumati River side | 4
11.1.2 | 2107 | Ravi Bhavan/Between Kalimati And Kalanki | 4
11.2.1 | 1550 | Kalanki | 4
11.2.2 | 1800 | Link Marg/Kuleshwor | 4
TU | 136 | TU area A,B,C | 4